## Sheet1
TABLE 8-1: REMEDIAL ALTERNATIVES EVALUATION SUMMARY
Alternative | Threshold Criteria |  | Balancing Criteria | [7 empty] | Modifying Criteria |  | Summary Rating
| Compliance with Permits and Applicable Regulatory Requirements |  | Long-Term Effectiveness in Protecting Human Health and the Environment and Achieving RAOs |  | Short-Term Effectiveness in Protecting Human Health and the Environment |  | Engineering Implementability, Reliability, Constructability, and Technical Feasibility |  | Cost |  | Stakeholder and Community Acceptance
| Rating | Rationale | Rating | Rationale | Rating | Rationale | Rating | Rationale | Rating | Estimate | Rating | Rationale
Alternative 1: No Action | 3 No Requirements |  | 0 Worst | Would not offer additional protectiveness relative to current conditions, would not prevent downstream transport of contaminants, and would not support removal of BUIs. | 1 Low | Would not create short-term impacts to human health or the environment, but would not address current risks in the short-term or the long-term. | 3 High | No action would be highly implementable from a logistical and technical perspective. | 3 Lowest Cost | 0 | 1 Worst | Not acceptable because does not achieve RAOs | 11
Alternative 2: Dry Excavation and Disposal | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements, which are expected to be similar to those for dry excavation in the Phase I area. | 3 High | Dry excavation with offsite disposal is expected to be the most effective technology for complete removal of sediments exceeding cleanup goals. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 3 High | Highly implementable in the shallow water environment of the Phase II area. Would produce the smallest volume of material for offsite disposal and involve faster and easier dewatering and water treatment. | 2 Moderate Cost | 14328000 | 3 High | Acceptable; public comments indicate support for an approach similar to the Phase I remediation. | 16
Alternative 2a: Dry Excavation and Disposal with Particle Size Segregation | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements. Requirements are expected to be similar to those for dry excavation in the Phase I area. | 3 High | See rationale for high effectiveness of Alternative 2a. Particle size segregation would not affect long-term protectiveness. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 2 Moderate | Although dry excavation is highly implementable in the shallow water environment of the Phase II area, the implementability and efficiency of particle size segregation is undetermined due to a high proportion of fine sediments. | 2 Moderate Cost | 14600000 | 3 High | Acceptable; public comments indicate support for an approach similar to the Phase I remediation. | 15
Alternative 3: Hydraulic Dredging and Disposal | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements. | 2 Moderate | Hydraulic dredging and offsite disposal would be generally effective, but with limited efficiency for removing material overlying hard surfaces, and tendency for suspension and redeposition of contaminated material. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 2 Moderate | Generally implementable, but would produce larger volumes of sediment for disposal, and larger amounts of water to be removed and treated. Dredge is also likely to encounter problems with debris behind the dam. | 1 High Cost | 17323000 | 2 Moderate | Acceptable; potential concerns regarding temporary dam and possible residual cover. | 12
Alternative 3a: Hydraulic Dredging and Disposal with Particle Size Segregation | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements. | 2 Moderate | See rationale for high effectiveness of Alternative 2b. Particle size segregation would not affect long-term protectiveness. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 1 Low | The implementability of hydraulic dredging is limited by the factors outlined for Alternative 2b, and the implementability and efficiency of particle size segregation is undetermined due to a high proportion of fine sediments. | 1 High Cost | 17941000 | 2 Moderate | Acceptable; potential concerns regarding temporary dam and possible residual cover. | 11
Alternative 4: Dry Excavation, Hydraulic Dredging, and Disposal | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements. | 3 High | Dredging of small volumes of sediment with a vacuum truck would not make this alternative significantly less effective than Alternative 2a. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 3 High | Dredging of small volumes of sediment with a vacuum truck would not make this alternative significantly less implementable than Alternative 2a. | 2 Low Cost | 13427000 | 3 High | Acceptable, based on public input received. | 16
Alternative 4a: Dry Excavation, Hydraulic Dredging, and Disposal with Particle Size Segregation | 3 Meets Criteria | Required permits would be obtained and remedial activities performed in compliance with their requirements. | 3 High | See rationale for high effectiveness of Alternative 2c. Particle size segregation would not affect long-term protectiveness. | 2 Moderate | Short-term risks to human health and the environment are similar for all sediment removal alternatives, and would be mitigated using PPE, site controls, and restoration activities following completion of the remedial action. | 2 Moderate | Dry excavation is highly implementable, and the implementability and efficiency of particle size segregation is undetermined due to a high proportion of fine sediments. Dredging of a small volume of sediments using a vacuum truck would only slightly decrease implementability, due to the factors outlined under Alternative 2b. | 2 Low Cost | 13684000 | 3 High | Acceptable, based on public input received. | 15
Note: Ratings are relative and intended to facilitate comparison of alternatives. 1 = worst; 3 = best.